## Detailed Task Estimates
No. | Task Name |  | Optimistic Effort | Most Likely Effort | Pessimistic Effort | Actual Effort | Plan Start Date | Plan End Date | Actual Start Date
| Requirement Analysis | Design Development | 8 | 8 | 12 |  | 2020-06-03 | 2020-06-04
| Design | Design Development | 16 | 16 | 24 |  | 2020-06-04 | 2020-06-08
Implementation - Development
| Environment Settings |  | 8 | 8 | 12 |  | 2020-06-08 | 2020-06-09
| Create the first model and datacontext | Code Development | 3 | 3 | 5 |  | 2020-06-09 | 2020-06-09
| Create database using entity framework migrations | Code Development | 3 | 3 | 5 |  | 2020-06-09 | 2020-06-09
| Retrieving data from the database | Code Development | 3 | 3 | 5 |  | 2020-06-10 | 2020-06-10
| Add Asynchronus | Code Development | 2 | 2 | 3 |  | 2020-06-10 | 2020-06-10
| Create Angular Application | Code Development | 1 | 1 | 2 |  | 2020-06-10 | 2020-06-10
| Add VS code extensions | Code Development | 1 | 1 | 2 |  | 2020-06-10 | 2020-06-10
| Making Http request in Angular | Code Development | 3 | 3 | 5 |  | 2020-06-11 | 2020-06-11
| Displaying data from API on Template | Code Development | 5 | 5 | 8 |  | 2020-06-11 | 2020-06-11
| Add BootStrap | Code Development | 2 | 2 | 3 |  | 2020-06-12 | 2020-06-12
| Add Git Source Controller | Code Development | 1 | 1 | 2 |  | 2020-06-12 | 2020-06-12
| Store Password in Database | Code Development | 2 | 2 | 3 |  | 2020-06-12 | 2020-06-12
| Create User Model | Code Development | 3 | 3 | 5 |  | 2020-06-12 | 2020-06-12
| Implement Repository Pattern | Code Development | 3 | 3 | 5 |  | 2020-06-15 | 2020-06-15
| Create Login - interface | Code Development | 4 | 4 | 6 |  | 2020-06-15 | 2020-06-15
| Create Login model | Code Development | 2 | 2 | 3 |  | 2020-06-15 | 2020-06-16
| Creating the login repository method | Code Development | 4 | 4 | 6 |  | 2020-06-16 | 2020-06-16
| Create Service and Register in Start up class | Code Development | 4 | 4 | 6 |  | 2020-06-16 | 2020-06-17
| Using DTOs | Code Development | 6 | 6 | 9 |  | 2020-06-17 | 2020-06-17
| Token Authentication | Code Development | 6 | 6 | 9 |  | 2020-06-17 | 2020-06-18
| Create login method in API | Code Development | 5 | 5 | 8 |  | 2020-06-18 | 2020-06-19
| Validate API | Code Development | 5 | 5 | 8 |  | 2020-06-19 | 2020-06-20
| Create Registration Model | Code Development | 5 | 5 | 8 |  | 2020-06-22 | 2020-06-22
| Create DTOs | Code Development | 3 | 3 | 5 |  | 2020-06-22 | 2020-06-23
| Add Service | Code Development | 5 | 5 | 8 |  | 2020-06-23 | 2020-06-23
| Add API Controlls | Code Development | 2 | 2 | 3 |  | 2020-06-23 | 2020-06-23
| Validate API | Code Development | 2 | 2 | 3 |  | 2020-06-23 | 2020-06-24
| Design Registration Template | Code Development | 5 | 5 | 8 |  | 2020-06-24 | 2020-06-24
| Add Angular Service | Code Development | 2 | 2 | 3 |  | 2020-06-24 | 2020-06-25
| Define Routes | Code Development | 3 | 3 | 5 |  | 2020-06-25 | 2020-06-25
| Add Resolvers | Code Development | 6 | 6 | 9 |  | 2020-06-25 | 2020-06-26
| Unit Testing | Code Rework | 8 | 8 | 12 |  | 2020-06-26 | 2020-06-29
Products - Page
| Create Model | Code Development | 5 | 5 | 8 |  | 2020-06-29 | 2020-06-29
| Create DTOs | Code Development | 5 | 5 | 8 |  | 2020-06-29 | 2020-06-30
| Add API Controlls | Code Development | 5 | 5 | 8 |  | 2020-06-30 | 2020-06-01
| Validate API with Token Authentication | Code Development | 5 | 5 | 8 |  | 2020-07-01 | 2020-07-01
| Add Angular Service | Code Development | 6 | 6 | 9 |  | 2020-07-01 | 2020-07-02
| Add Resolver | Code Development | 3 | 3 | 5 |  | 2020-07-02 | 2020-07-02
| Add Router Path | Code Development | 3 | 3 | 5 |  | 2020-07-02 | 2020-07-03
| Design Template | Code Development | 8 | 8 | 12 |  | 2020-07-03 | 2020-07-06
| Validate Component | Code Development | 5 | 5 | 8 |  | 2020-07-06 | 2020-07-06
| Unit Testing | Code Rework | 8 | 8 | 12 |  | 2020-07-06 | 2020-07-07
Like - Page
| Create Model | Code Development | 5 | 5 | 8 |  | 2020-07-07 | 2020-07-08
| Create DTOs | Code Development | 5 | 5 | 8 |  | 2020-07-08 | 2020-07-09
| Add API Controlls | Code Development | 5 | 5 | 8 |  | 2020-07-09 | 2020-07-09
| Validate API | Code Development | 5 | 5 | 8 |  | 2020-07-09 | 2020-07-10
| Add Angular Service | Code Development | 6 | 6 | 9 |  | 2020-07-10 | 2020-07-13
| Add Resolver | Code Development | 3 | 3 | 5 |  | 2020-07-13 | 2020-07-13
| Add Router Path | Code Development | 3 | 3 | 5 |  | 2020-07-13 | 2020-07-13
| Design Template | Code Development | 8 | 8 | 12 |  | 2020-07-13 | 2020-07-14
| Validate Component | Code Development | 5 | 5 | 8 |  | 2020-07-14 | 2020-07-15
| Unit Testing | Code Rework | 8 | 8 | 12 |  | 2020-07-15 | 2020-07-16
Cart - Page
| Create Model | Code Development | 5 | 5 | 8 |  | 2020-07-16 | 2020-07-17
| Create DTOs | Code Development | 5 | 5 | 8 |  | 2020-07-17 | 2020-07-17
| Add API Controlls | Code Development | 5 | 5 | 8 |  | 2020-07-17 | 2020-07-18
| Validate API with Token Authentication | Code Development | 5 | 5 | 8 |  | 2020-07-18 | 2020-07-18
| Add Angular Service | Code Development | 6 | 6 | 9 |  | 2020-07-18 | 2020-07-20
| Add Resolver | Code Development | 3 | 3 | 5 |  | 2020-07-20 | 2020-07-20
| Add Router Path | Code Development | 3 | 3 | 5 |  | 2020-07-21 | 2020-07-21
| Design Template | Code Development | 8 | 8 | 12 |  | 2020-07-21 | 2020-07-22
| Validate Component | Code Development | 5 | 5 | 8 |  | 2020-07-22 | 2020-07-23
| Unit Testing | Dev Testing | 8 | 8 | 12 |  | 2020-07-23 | 2020-07-24
Payment - Page
| Create Model | Code Development | 5 | 5 | 8 |  | 2020-07-24 | 2020-07-24
| Create DTOs | Code Development | 5 | 5 | 8 |  | 2020-07-25 | 2020-07-25
| Add API Controlls | Code Development | 5 | 5 | 8 |  | 2020-07-25 | 2020-07-27
| Validate API with Token Authentication | Code Development | 5 | 5 | 8 |  | 2020-07-27 | 2020-07-27
| Add Angular Service | Code Development | 6 | 6 | 9 |  | 2020-07-27 | 2020-07-28
| Add Resolver | Code Development | 3 | 4 | 6 |  | 2020-07-28 | 2020-07-28
| Add Router Path | Code Development | 3 | 4 | 6 |  | 2020-07-28 | 2020-07-29
| Design Template | Code Development | 8 | 8 | 12 |  | 2020-07-29 | 2020-07-30
| Validate Component | Code Development | 5 | 5 | 8 |  | 2020-07-30 | 2020-07-30
| Unit Testing | Dev Testing | 8 | 8 | 12 |  | 2020-08-02 | 2020-08-03
Message Page
| Create Model | Code Development | 8 | 8 | 12 |  | 2020-08-03 | 2020-08-04
| Create DTOs | Code Development | 8 | 8 | 12 |  | 2020-08-04 | 2020-08-05
| Create Components | Code Development | 5 | 5 | 8 |  | 2020-08-05 | 2020-08-05
| Design Template | Code Development | 8 | 8 | 12 |  | 2020-08-05 | 2020-08-06
| Unit Testing | Dev Testing | 8 | 8 | 12 |  | 2020-08-06 | 2020-08-07
| UI Testing | Testing | 24 | 24 | 36 |  | 2020-08-07 | 2020-08-09
| API Testing | Testing | 24 | 24 | 36 |  | 2020-08-09 | 2020-08-12
| Publish Website | Deployment | 12 | 12 | 12 |  | 2020-08-12 | 2020-08-14
|  |  | 450 | 430 | 694

## Task BreakDown(Weekly )
Task Name | Start Date | End Date | Week One
Environment Settings | 2020-06-08 | 2020-06-09
Create the first model and datacontext | 2020-06-09 | 2020-06-09
Create database using entity framework migrations | 2020-06-09 | 2020-06-09
Retrieving data from the database | 2020-06-10 | 2020-06-10
Add Asynchronus | 2020-06-10 | 2020-06-10
Create Angular Application | 2020-06-10 | 2020-06-10
Add VS code extensions | 2020-06-10 | 2020-06-10
Making Http request in Angular | 2020-06-11 | 2020-06-11
Displaying data from API on Template | 2020-06-11 | 2020-06-11
Add BootStrap | 2020-06-12 | 2020-06-12
Add Git Source Controller | 2020-06-12 | 2020-06-12
Store Password in Database | 2020-06-12 | 2020-06-12
Create User Model | 2020-06-12 | 2020-06-12
Task Name | Start Date | End Date | week two
Implement Repository Pattern | 2020-06-15 | 2020-06-15
Create Login - interface | 2020-06-15 | 2020-06-15
Create Login model | 2020-06-15 | 2020-06-16
Creating the login repository method | 2020-06-16 | 2020-06-16
Create Service and Register in Start up class | 2020-06-16 | 2020-06-17
Using DTOs | 2020-06-17 | 2020-06-17
Token Authentication | 2020-06-17 | 2020-06-18
Create login method in API | 2020-06-18 | 2020-06-19
Validate API | 2020-06-19 | 2020-06-20

## Sheet1
No | Task Name | Progress % | Time Spent (Hrs) | Comment | Status
1 | Implement Repository Pattern | 100 | 1 | Repository patter is decouple data access layer and business layer | on track
2 | Create Login - interface | 100 | 1 |  | on track
| Create Login model | 100 | 4 |  | on track
| Create User Model | 100 | 1 |  | on track
Resource Name | GIT URL | Google/One Drive URL
Online Home Shop | https://github.com/tharindubandaraD/OnlineHomeShop | -

## Assumption
Assumptions (List out all assumptions related to the estimates)
Please Note: All kinds of assumptions that have an impact on the project estimates and project schedule should be documented and their corresponding impact assessed and aligned to the estimate
Re-use Related Assumptions |  | 0 | Assumptions
No. | Description
1 | Unit- testing : Need to go with unit testing approch.
2 | UI Testing : No any previous expereince
3 | API Testing : No any previous expereince
4 | Deployment: No any previous expereince
5
6
7